## Milestones - Consolidated
CoreoView User Guide Plan
					Sep-19					Oct-19					Nov-19					Dependencies
Milestones	RAG Status	Responsible	Planned Start Dt	Planned End Dt	11	12	13	16	17	18	19	20	23	24	25	26	27	30	1	3	4	7	9	10	11	14	15	16	17	18	21	22	23	24	25	29	30	31	4	5	6	7	8	11	12	13	14	15	18	19	20	21	22	25	26	27	28	29	2	3	4	5	6	9	10
Complete training and knowledge transfer on CoreoView for product knowledge	On going	SMEs/Piyush					Piyush/SMEs – I need periodic knowledge transfer from Piyush (BA); Please note, its very important to have periodic KTs from Piyush
Template finalization	Complete	Pavan	Wed, Sep-11-19	Fri Sep-13-19
Template finalization- Incorporate review comments from Jeff and Josh	To Start	Pavan	Fri, Sep-27-19	Fri, Sep-27-19
Document outline	Complete	Pavan	Mon, 09-16-19	Tue 09-17-19
Document outline - Internal review	To Start	Piyush/SMEs	Tue, 09-17-19	Tue 09-17-19
Document outline - Work on internal review comments	To Start	Pavan	Tue, 09-17-19	Tue 09-17-19
Document outline - Review with Jeff and Josh	To Start	Jeff and Josh	Fri, Sep-27-19	Fri, Sep-27-19
Document outline - Incorporate review comments from Jeff and Josh	To Start	Pavan	Mon Sep-30-19	Mon Sep-30-19
Configure CoreoView Environment for user guide screenshots	To Start	Dev Team	Mon, 09-23-19	Mon 09-23-19
Few sub-sections of the user's guide	Complete	Pavan	Thu Sep-19-19	Fri, Sep-20-19
First and second chapters of the user's guide	Started	Pavan	Mon Sep-23-19	Wed 09-25-19
First and second chapters of the user's guide - Internal review	To Start	Piyush/SMEs	Thu, 09-26-19	Thu, 09-26-19
First and second chapters of the user's guide - Work on internal review comments	To Start	Pavan	Thu, 09-26-19	Fri 09-27-19
First and second chapters of the user's guide - Review with Jeff and Josh	To Start	Jeff and Josh	Fri, 09-27-19	Fri 09-27-19
First and second chapters of the user's guide - Incorporate review comments from Jeff and Josh	To Start	Pavan	Mon, 09-30-19	Mon, 09-30-19
Identify Mini workflows for CV	To Start	Piyush/SMEs					As per Rachit's inputs, the functional team/Piyush should be able to work on the mini workflows and the dates have to be finalized based on the client's inputs.
Half way completion of the user's guide	To Start	Pavan	Tue, Oct-1-19	Tue, Oct-15-19
Half way completion of the user's guide - Internal review	To Start	Piyush/SMEs	Wed, Oct-16-19	Wed, Oct-16-19
Half way completion of the user's guide - Work on internal review comments	To Start	Pavan	Thu, Oct-17-19	Fri, Oct-18-19
Half way completion of the user's guide -Review with Jeff and Josh	To Start	Jeff and Josh	Mon, Oct-21-19	Mon, Oct-21-19
Half way completion of the user's guide - Incorporate review comments from Jeff & Josh	To Start	Pavan	Tue, Oct-22-19	Wed, Oct-23-19
Final Draft of CoreoView user's guide	To Start	Pavan	Thu, Oct-24-19	Mon, Nov-11-19
Final Draft of CoreoView user's guide - Internal review	To Start	Piyush/SMEs	Tue, Nov-12-19	Wed, Nov-13-19
Final Draft of CoreoView user's guide - Work on Internal review comments	To Start	Pavan	Thu, Nov-14-19	Mon, Nov-18-19
Final Draft of CoreoView user's guide - Review with Jeff and Josh	To Start	Jeff and Josh	Tue, Nov-19-19	Tue, Nov-19-19
Final Draft of CoreoView user's guide - Incorporate review comments from Jeff and Josh	To Start	Pavan	Wed, Nov-20-19	Thu, Nov-21-18
CoreoView user's guide - PDF	To Start	Pavan	Fri, Nov-22-19	Mon, Nov-25-19
CoreoView user's guide - PDF - Review with Jeff and Josh	To Start	Jeff and Josh	Tue, Nov-26-19	Tue, Nov-26-19
CoreoView user's guide - PDF - Incorporate review comments from Jeff and Josh	To Start	Pavan	Wed, Nov-27-19	Thu, Nov-28-19
Final handover CoreoView user's guide	To Start	Pavan	Fri, Nov-29-19	Fri, Nov-29-19
Final handover - Proposed date by Jeff and Josh				Wed, Dec-04-19
Prepare a similar plan for CoreoHome user's guide	To Start	Pavan	Mon, Dec-02-19	Wed, Dec-04-19