## Project Milestones
CoreoView User's Guide - Project Milestones
Project Milestones | No | Task | Planned Start Date | Planned End Date | Status (R/A/G) | Status Comments - 1 | Comments - 2
Template finalization | 1 | Review with Jeff and Josh | Tue 09-17-19 | Tue 09-17-19 |  | Awaiting review comments from Jeff and Josh
Document outline | 1 | Review with Jeff and Josh | Tue 09-17-19 | Tue 09-17-19 |  |  | This document covers all the features and functionalities that must be written in the user guide. Lists the topic-titles and sub-titles
| 2 | Incorporate the comments | Mon 09-23-19 | Mon 09-23-19
Mini workflows | 1 | Review with Jeff and Josh | Mon 09-30-19 | Mon 09-30-19
| 2 | Incorporate the comments | Fri 10-04-19 | Fri 10-04-19
First chapter of the user's guide | 1 | Review with Jeff and Josh | Mon 10-14-19 | Mon 10-14-19 |  |  | The inclusion of the screenshots is subject to the availability of the final CoreoView environment.
| 2 | Incorporate the comments | Fri 10-18-19 | Fri 10-18-19
Half way completion of the user's guide | 1 | Review with Jeff and Josh | Mon 10-28-19 | Mon 10-28-19 |  |  | Review of the user's guide at 50% completion - optional milestone - Left to the discretion of Jeff and Josh
| 2 | Incorporate the comments | Mon 11-04-19 | Mon 11-04-19
Final Draft-CoreoView user's guide | 1 | Review with Jeff and Josh | Tue 11-19-19 | Tue 11-19-19
| 2 | Incorporate the comments | Mon 11-25-19 | Mon 11-25-19
CoreoView user's guide - PDF | 1 | Final Draft - Review with Jeff and Josh | Thu 11-28-19 | Thu 11-28-19
Final handover |  | Final handover | Wed 12-04-19 | Wed 12-04-19